## Sheet1
Timeline | Action Item | Functionality | Start Date | End Date | Duration (Days) | Status
Design | Standardized RIDE usage → Shared single truth | All data is unified so users see same data everywhere. | Mar-20-2026 | Mar-23-2026 | 2 | Planned
Design | Mandatory ownership practice → Clear accountability | Every task has an owner and responsibility is clearly visible. | Mar-24-2026 | Mar-25-2026 | 2 | Planned
Design | Daily live tracking → Faster awareness | Users see real-time updates without refreshing. | Mar-26-2026 | Mar-27-2026 | 2 | Planned
Design | Non-editable audit history → Governance confidence | All changes are stored and cannot be modified. | Mar-30-2026 | Mar-31-2026 | 2 | Planned
Design | Risk trending → Early warning | Shows risk increase over time so users can act early. | Apr-01-2026 | Apr-02-2026 | 2 | Planned
Design | Escalation aging → Stagnation exposed | Shows tasks stuck for long time and highlights them. | Apr-03-2026 | Apr-06-2026 | 2 | Planned
Design | Dependency signals → Delay prevention | Shows impact of delayed tasks on other tasks. | Apr-07-2026 | Apr-08-2026 | 2 | Planned
Design | Closure velocity → Capacity balance | Shows how fast work is getting completed. | Apr-09-2026 | Apr-10-2026 | 2 | Planned
Design | Policy rules → Auto enforcement | System automatically enforces rules and validations. | Apr-13-2026 | Apr-14-2026 | 2 | Planned
Design | Auto-escalations → Timely intervention | Escalates tasks automatically when needed. | Apr-15-2026 | Apr-16-2026 | 2 | Planned
Design | Portfolio correlation → Systemic clarity | Shows overall performance across projects. | Apr-17-2026 | Apr-20-2026 | 2 | Planned
Design | Decision guidance → Predictable outcomes | Suggests what action to take based on data. | Apr-21-2026 | Apr-22-2026 | 2 | Planned
Design | Auto project creation → Admin-governed templates | Creates projects automatically with predefined setup. | Apr-23-2026 | Apr-24-2026 | 2 | Planned
Design | Aging triggers | Triggers alert when task is inactive for long time. | Apr-27-2026 | Apr-28-2026 | 2 | Planned
Design | Predictive alerts | Alerts users before issues happen. | Apr-29-2026 | Apr-30-2026 | 2 | Planned
Design | Auto escalations | Automatically escalates based on conditions. | May-01-2026 | May-04-2026 | 2 | Planned
Design | SLA enforcement | Ensures deadlines are followed and alerts on delay. | May-05-2026 | May-06-2026 | 2 | Planned
Design | Risk trend detection | Detects unusual increase in risks. | May-07-2026 | May-08-2026 | 2 | Planned
Development | Standardized RIDE usage → Shared single truth | All data is unified so users see same data everywhere. | May-11-2026 | May-13-2026 | 3 | Planned
Development | Mandatory ownership practice → Clear accountability | Every task has an owner and responsibility is clearly visible. | May-14-2026 | May-18-2026 | 3 | Planned
Development | Daily live tracking → Faster awareness | Users see real-time updates without refreshing. | May-19-2026 | May-21-2026 | 3 | Planned
Development | Non-editable audit history → Governance confidence | All changes are stored and cannot be modified. | May-22-2026 | May-26-2026 | 3 | Planned
Development | Risk trending → Early warning | Shows risk increase over time so users can act early. | May-27-2026 | May-29-2026 | 3 | Planned
Development | Escalation aging → Stagnation exposed | Shows tasks stuck for long time and highlights them. | Jun-01-2026 | Jun-03-2026 | 3 | Planned
Development | Dependency signals → Delay prevention | Shows impact of delayed tasks on other tasks. | Jun-04-2026 | Jun-08-2026 | 3 | Planned
Development | Closure velocity → Capacity balance | Shows how fast work is getting completed. | Jun-09-2026 | Jun-11-2026 | 3 | Planned
Development | Policy rules → Auto enforcement | System automatically enforces rules and validations. | Jun-12-2026 | Jun-16-2026 | 3 | Planned
Development | Auto-escalations → Timely intervention | Escalates tasks automatically when needed. | Jun-17-2026 | Jun-19-2026 | 3 | Planned
Development | Portfolio correlation → Systemic clarity | Shows overall performance across projects. | Jun-22-2026 | Jun-24-2026 | 3 | Planned
Development | Decision guidance → Predictable outcomes | Suggests what action to take based on data. | Jun-25-2026 | Jun-29-2026 | 3 | Planned
Development | Auto project creation → Admin-governed templates | Creates projects automatically with predefined setup. | Jun-30-2026 | Jul-02-2026 | 3 | Planned
Development | Aging triggers | Triggers alert when task is inactive for long time. | Jul-03-2026 | Jul-07-2026 | 3 | Planned
Development | Predictive alerts | Alerts users before issues happen. | Jul-08-2026 | Jul-10-2026 | 3 | Planned
Development | Auto escalations | Automatically escalates based on conditions. | Jul-13-2026 | Jul-15-2026 | 3 | Planned
Development | SLA enforcement | Ensures deadlines are followed and alerts on delay. | Jul-16-2026 | Jul-20-2026 | 3 | Planned
Development | Risk trend detection | Detects unusual increase in risks. | Jul-21-2026 | Jul-23-2026 | 3 | Planned
Testing (Both) | Standardized RIDE usage → Shared single truth & Mandatory ownership practice → Clear accountability | Validate both features together end-to-end | Jul-24-2026 | Jul-27-2026 | 2 | Planned
Testing (Both) | Daily live tracking → Faster awareness & Non-editable audit history → Governance confidence | Validate both features together end-to-end | Jul-28-2026 | Jul-29-2026 | 2 | Planned
Testing (Both) | Risk trending → Early warning & Escalation aging → Stagnation exposed | Validate both features together end-to-end | Jul-30-2026 | Jul-31-2026 | 2 | Planned
Testing (Both) | Dependency signals → Delay prevention & Closure velocity → Capacity balance | Validate both features together end-to-end | Aug-03-2026 | Aug-04-2026 | 2 | Planned
Testing (Both) | Policy rules → Auto enforcement & Auto-escalations → Timely intervention | Validate both features together end-to-end | Aug-05-2026 | Aug-06-2026 | 2 | Planned
Testing (Both) | Portfolio correlation → Systemic clarity & Decision guidance → Predictable outcomes | Validate both features together end-to-end | Aug-07-2026 | Aug-10-2026 | 2 | Planned
Testing (Both) | Auto project creation → Admin-governed templates & Aging triggers | Validate both features together end-to-end | Aug-11-2026 | Aug-12-2026 | 2 | Planned
Testing (Both) | Predictive alerts & Auto escalations | Validate both features together end-to-end | Aug-13-2026 | Aug-14-2026 | 2 | Planned
Testing (Both) | SLA enforcement & Risk trend detection | Validate both features together end-to-end | Aug-17-2026 | Aug-18-2026 | 2 | Planned